## Build Plan
# | Feature | Phase | Priority | P&L Impact | Build Time | Cost | External Resources? | Free Alternative | Status | Key Files to Modify | Dependencies
PHASE 1: SPEED UP SCANS + MAXIMIZE TRADE VOLUME (Weeks 1-2)
1 | IBKR Streaming Data (replace yfinance primary) | Phase 1 | CRITICAL | HIGH | 3-5 days | FREE | No - IBKR delayed data is free on paper account | Already have it: reqMktData type 3 (15-min delayed) is free. reqMktData type 1 needs $1-15/mo subscription | TODO | signals.py, scanner.py, bot.py | ib_async already installed
2 | Parallel yfinance with process isolation | Phase 1 | CRITICAL | HIGH | 2-3 days | FREE | No - pure Python refactor | Use multiprocessing.Pool (separate processes avoid yfinance thread-safety). Each symbol in its own process = no data contamination | TODO | signals.py (score_universe) | None
3 | Lower score thresholds for paper trading | Phase 1 | HIGH | N/A (data) | 1 hour | FREE | No - config change only | Set min_score_to_trade=18, agents_required_to_agree=2 during paper phase to generate 5-10x more trades for training data | TODO | config.py | None
4 | Reduce scan intervals during prime hours | Phase 1 | HIGH | MEDIUM | 1 hour | FREE | No - config change only | scan_interval_prime=3 (from 5), scan_interval_standard=5 (from 10). More scans = more opportunities caught | TODO | config.py | None
5 | Relax TV pre-filter (too aggressive) | Phase 1 | HIGH | MEDIUM | 2-3 hours | FREE | No - pure code change | Current filter kills RSI 42-58 and change < 0.3%. This drops breakout setups and mean-reversion plays. Widen to RSI 35-65, change > 0.1% | TODO | bot.py (run_scan, lines 1325-1335) | None
6 | Add batch IBKR price fetching | Phase 1 | MEDIUM | MEDIUM | 1-2 days | FREE | No - use reqTickers with contract list | reqTickers can take a list of contracts. Fetch all prices in one call instead of one-by-one in execute_buy | TODO | orders.py | None
7 | Cache TradingView data between scans | Phase 1 | MEDIUM | LOW | 3-4 hours | FREE | No - in-memory cache | TV screener data is already fetched. Cache with TTL=2min so regime detection and pre-filter don't re-fetch | TODO | scanner.py | None
PHASE 2: HISTORICAL DATA + BACKTESTING ENGINE (Weeks 2-4)
8 | Backtesting engine (replay historical data through signal pipeline) | Phase 2 | CRITICAL | CRITICAL | 2 weeks | FREE | No - yfinance historical data is free | Refactor signals.py to accept DataFrame instead of downloading. Replay 1yr of 5m data for top 50 symbols. Log simulated trades to SQLite | TODO | NEW: backtest.py, signals.py refactor | yfinance, sqlite3
9 | Performance attribution (P&L by regime, score, time, agent) | Phase 2 | CRITICAL | HIGH | 3-5 days | FREE | No - pure math on existing trade log | Break down trades.json by: regime, score bucket (20-30, 30-40, 40-50), time of day, hold duration, agent agreement count | TODO | NEW: attribution.py, learning.py | pandas, matplotlib
10 | Historical data pipeline (yfinance + Alpha Vantage + Stooq) | Phase 2 | HIGH | HIGH | 1 week | FREE | Alpha Vantage free tier: 25 calls/day. Stooq: unlimited daily OHLCV. yfinance: 1yr of 5m data, 5yr of 1d data | yfinance for intraday (5m bars, 60 days). Alpha Vantage for daily OHLCV (20yr free). Stooq for bulk daily downloads. Layer all 3 for coverage | TODO | NEW: data_pipeline.py | requests, pandas
11 | Walk-forward optimization framework | Phase 2 | HIGH | HIGH | 1 week | FREE | No - pure Python with Optuna | Train on 6 months, test on 1 month, roll forward. Optimize: score thresholds, ATR multipliers, position sizing. Use Optuna (free) | TODO | NEW: optimize.py | optuna (pip install optuna)
12 | Synthetic trade generation (backtest paper trades across regimes) | Phase 2 | HIGH | CRITICAL | 1 week | FREE | No - uses backtester output | Run backtester across Jan-Mar 2024 (bull), Aug-Oct 2023 (choppy), Mar 2020 (panic), 2022 (bear). Generates 500+ synthetic trades for ML training | TODO | Uses backtest.py | Backtester (item 8)
PHASE 3: ML CLASSIFIER + ADAPTIVE LEARNING (Weeks 4-6)
13 | XGBoost signal classifier (trained on backtest data) | Phase 3 | CRITICAL | CRITICAL | 1 week | FREE | No - pip install xgboost is free | Features: 7 signal dimensions + regime + time_of_day + vol_ratio + news_score. Target: trade profitable Y/N. Needs 200+ trades from backtester | TODO | NEW: ml_classifier.py, signals.py integration | xgboost, scikit-learn
14 | Agent accuracy tracking per agent | Phase 3 | HIGH | HIGH | 3-5 days | FREE | No - logging enhancement | Track each agent's BUY/SELL recommendation vs actual outcome. Find which agents are right/wrong and weight their votes accordingly | TODO | agents.py, learning.py | None
15 | Auto-retrain monthly with new trade data | Phase 3 | HIGH | HIGH | 3-5 days | FREE | No - scheduled retraining | Every 30 days: retrain XGBoost on last 90 days of trades. Update scoring thresholds based on what's actually profitable. Log before/after metrics | TODO | NEW: retrain.py, schedule in bot.py | xgboost
16 | Dynamic correlation matrix (replace hard-coded sectors) | Phase 3 | MEDIUM | MEDIUM | 2-3 days | FREE | No - numpy on yfinance data | Rolling 30-day correlation between all held symbols. Alert when portfolio correlation > 0.7. Auto-reduce sizing for correlated adds | TODO | risk.py | numpy
PHASE 4: SOCIAL SENTIMENT + ALTERNATIVE DATA (Weeks 5-7)
17 | Reddit sentiment (r/wallstreetbets + r/stocks) | Phase 4 | HIGH | HIGH | 3-5 days | FREE | Reddit JSON API: free, no key needed (100 req/min). PRAW library for structured access (free API key) | Hit /r/wallstreetbets/new.json. Track: mention velocity, upvote ratio, sentiment (VADER + finance lexicon). Plug into news_sentinel.py as source #4 | TODO | news_sentinel.py, NEW: reddit_sentiment.py | praw or requests
18 | ApeWisdom API integration (pre-computed WSB sentiment) | Phase 4 | MEDIUM | MEDIUM | 1 day | FREE | No - ApeWisdom API is free, no key needed | apewisdom.io/api/ returns top mentioned tickers with sentiment. One API call replaces manual scraping. Updates every 30 min | TODO | news_sentinel.py | requests
19 | SEC EDGAR filing monitor (insider trades, 13F) | Phase 4 | MEDIUM | MEDIUM | 3-5 days | FREE | No - SEC EDGAR RSS is public/free | Monitor SEC RSS for Form 4 (insider buys/sells) and 8-K (material events). Insider buying clusters are one of strongest alpha signals. SEC has no rate limit on RSS | TODO | NEW: sec_monitor.py, news_sentinel.py | requests, xml.etree
20 | Google Trends integration (search interest spikes) | Phase 4 | LOW | MEDIUM | 1-2 days | FREE | No - pytrends library is free | pytrends tracks Google search volume. Spike in '[ticker] stock' searches often precedes retail inflows by hours. Good leading indicator for meme stocks | TODO | news_sentinel.py | pytrends
PHASE 5: EXECUTION + ADVANCED FEATURES (Weeks 6-10)
21 | IBKR native algo orders (TWAP/VWAP/Adaptive) | Phase 5 | HIGH | HIGH | 2-3 days | FREE | No - IBKR algo orders are free on paper accounts | Replace LimitOrder with IBAlgoOrder(algoStrategy='Adaptive'). IBKR handles TWAP/VWAP execution natively. One parameter change per order | TODO | orders.py | ib_async
22 | Multi-round agent debate (bull vs bear) | Phase 5 | MEDIUM | MEDIUM | 3-5 days | ~$1/scan extra | No new tools - just more Claude API calls | Add BullResearcher + BearResearcher agents between Opportunity and Devil's Advocate. 2 rounds of challenge/response. TradingAgents (ICML) proved this works | TODO | agents.py | anthropic API
23 | Options spread strategies (verticals, iron condors) | Phase 5 | MEDIUM | MEDIUM | 2 weeks | FREE | No - IBKR supports multi-leg options on paper | Add bull call spreads and iron condors. Reduce cost basis 40-60%. Better defined risk than single-leg. Use existing options.py Greeks engine | TODO | options.py, orders.py | ib_async
24 | Direct short selling (replace inverse ETF workaround) | Phase 5 | MEDIUM | MEDIUM | 1 week | FREE | No - IBKR paper supports short selling | Use IBKR short locate and sell short. Eliminates 3x leverage decay from SPXS/SQQQ. Add pairs trading (long/short correlated stocks) | TODO | orders.py, risk.py | ib_async
25 | Intraday regime micro-shifts (TICK, ADD, VOLD) | Phase 5 | LOW | MEDIUM | 1 week | FREE* | IBKR provides TICK-NYSE, ADD-NYSE, VOLD-NYSE as streaming data. May need $1/mo NYSE data addon | Track breadth indicators for 15-min regime shifts. Current regime updates hourly = too slow for intraday reversals | TODO | scanner.py, risk.py | ib_async

## Training Data Sources
Source | Data Type | Cost | Coverage | Granularity | API Key? | Rate Limit | How to Use in Decifer | Reliability
yfinance (current) | OHLCV + Fundamentals | FREE | All US stocks, ETFs, indices, crypto | 1m (7d), 5m (60d), 1d (unlimited) | No | ~2000/hr (throttled) | Already using. Keep for backtesting historical 5m data. 60 days of 5m bars per symbol = good for backtest | MEDIUM - crumb errors, thread-safety issues
Alpha Vantage | OHLCV Daily/Intraday | FREE (25/day) | US stocks, FX, crypto | 1min-daily. Daily: 20+ years free | Yes (free signup) | 25 calls/day (free), 75/min (premium $50/mo) | Use for DAILY historical bars going back 20 years. Supplement yfinance for long-term backtesting. Don't use for real-time | HIGH - stable API, rarely down
Stooq | Daily OHLCV bulk | FREE | US, EU, Asia stocks + indices | Daily only. 20+ years | No | None (download CSVs) | Bulk download daily OHLCV for entire US market. Use for broad backtesting and correlation analysis. Download once, store locally | HIGH - very reliable, been around 15+ years
IBKR Historical Data | OHLCV + tick | FREE (paper) | Everything IBKR trades | 1sec to monthly. 1yr of 1m bars free | No (use ib_async) | 60 requests/10min | reqHistoricalData in ib_async. Get 1-minute bars for last year. Best quality intraday data available to you. Use for backtest validation | VERY HIGH - exchange-sourced
Databento | OHLCV + L2 + trades | $125 free credit | US equities, futures, options | Tick to daily | Yes (free signup) | Credit-based | Use $125 credit for high-quality tick data on your top 20 symbols. Good for order flow analysis research. One-time use | VERY HIGH - institutional grade
Reddit JSON API | Post titles, scores, comments | FREE | All subreddits | Real-time | No (or free PRAW key) | 100 req/min (no key), 60/min (with key) | Hit /r/wallstreetbets/new.json and /r/stocks. Parse titles for ticker mentions. Track mention velocity + VADER sentiment. Plug into news_sentinel as source #4 | HIGH - Reddit rarely blocks JSON
ApeWisdom API | Pre-computed WSB sentiment | FREE | r/wallstreetbets, r/stocks, r/crypto | Updates every 30 min | No | None documented | apewisdom.io/api/v1.0/filter/all-stocks returns top 50 mentioned tickers with rank, mentions_24h, upvotes. One call replaces manual scraping | MEDIUM - third-party service
SEC EDGAR RSS | Insider trades, 8-K, 13F | FREE | All SEC filings | Real-time (minutes after filing) | No | 10 req/sec | Monitor Form 4 (insider buys), 8-K (material events), 13F (institutional holdings). RSS feed at sec.gov/cgi-bin/browse-edgar. Strongest free alpha signal | VERY HIGH - government source
Yahoo Finance RSS | News headlines | FREE | All US stocks | Near real-time | No | Reasonable | Already using in news_sentinel.py. Keep as-is. Consider adding Yahoo Finance trending tickers endpoint for additional signal | MEDIUM - occasional 403s
Finviz | News + screener | FREE | US stocks | Near real-time (scrape) | No | Be polite (1 req/sec) | Already using in news_sentinel.py. Add Finviz screener tables (insider ownership, analyst targets, earnings dates) for enrichment | MEDIUM - scraping can break
IBKR News | Benzinga, DJ, FlyOnWall | FREE (paper) | US stocks | Real-time | No (use ib_async) | Reasonable | Already using in news_sentinel.py. This is your BEST news source - real-time, multi-provider. Increase polling frequency | HIGH - professional feeds
Google Trends (pytrends) | Search interest over time | FREE | Global | Daily, weekly, real-time | No | Throttled (~10/min) | Track search volume for stock tickers. Spikes precede retail buying waves. Use as early warning in sentiment scoring | MEDIUM - Google can throttle
Quandl/Nasdaq Data Link | Economic indicators | FREE tier | US macro data (GDP, CPI, unemployment) | Various | Yes (free signup) | 50 calls/day (free) | Feed macro data into regime detection. Add CPI surprise, PMI, jobless claims as features for ML classifier | HIGH

## Scan Speed Analysis
Step | Current Time | Bottleneck? | Root Cause | Fix | Expected Time After Fix | Priority
1. Regime detection (SPY/QQQ/VIX) | 5-10 sec | MINOR | 3 sequential yfinance downloads (SPY, QQQ, VIX) | Use IBKR reqMktData for SPY/QQQ/VIX prices (already connected). Fall back to yfinance only if IBKR fails | 1-2 sec | HIGH
2. TradingView screener (6 queries) | 3-8 sec | NO | TV screener is fast and parallel. 6 queries complete in seconds | Keep as-is. This is well-optimized already | 3-8 sec | NONE
3. TV pre-filter (rank + filter) | < 1 sec | YES (over-filtering) | Kills too many symbols: RSI 42-58 dead zone, change < 0.3%, rel_vol < 1.0. Drops valid breakout/reversal setups | Widen filters: RSI 35-65, change > 0.1%, rel_vol > 0.8. Let more symbols through to yfinance scoring | < 1 sec | HIGH
4. News sentiment (Yahoo RSS batch) | 5-15 sec | MINOR | Sequential RSS fetches for up to 50 symbols. Each takes 0.3-1.5 sec | Already uses ThreadPoolExecutor(max_workers=10). Could increase to 15. Or reduce batch to top 20 symbols | 3-8 sec | LOW
5. score_universe (yfinance multi-TF) | 180-240 sec | CRITICAL | max_workers=1 (sequential). Each symbol = 3 yfinance downloads (5m, 1d, 1wk). 15 symbols x 3 downloads x ~4 sec = 180 sec | Option A: multiprocessing.Pool (separate processes, thread-safe). Option B: IBKR reqHistoricalData for 5m bars. Option C: Cache daily/weekly data (only changes once/day) | 30-60 sec | CRITICAL
6. Options scanner | 30-60 sec | MODERATE | ThreadPoolExecutor(max_workers=6) but yfinance option_chain is slow (2-5 sec per symbol, 40+ symbols) | Reduce OPTIONABLE_UNIVERSE to top 25. Only scan symbols that also scored well in step 5. Skip if no options-enabled signals | 10-20 sec | MEDIUM
7. 6-agent Claude pipeline | 45-90 sec | MODERATE | 6 sequential Claude API calls @ 800 tokens each. ~8-15 sec per call | Agents 1-3 (Technical, Macro, Opportunity) can run in parallel since they read the same data. Only 4-6 need to be sequential. Already partially parallelized (max_workers=2) | 30-50 sec | MEDIUM
8. Order execution | 2-5 sec | NO | Fast. IBKR limit orders submit quickly | Keep as-is. Add IBKR algo orders later (Phase 5) | 2-5 sec | NONE
TOTAL SCAN CYCLE | 4-7 min | YES | Step 5 (yfinance scoring) is 60-70% of total time | Fix step 5 → total drops to ~2-3 min. Fix steps 1+5+6 → ~1.5-2 min | 1.5-3 min | CRITICAL

## Trade Volume Strategy
Change | Current Setting | Proposed Setting | Effect on Trade Volume | Risk | Reversible?
CONFIG CHANGES (Paper Trading Only - Maximize Data Collection)
Lower min_score_to_trade | 28 (bull), 25 (bear/unknown) | 18 (all regimes) | 5-10x more trades per day. Currently most symbols score 20-27 and get dropped. These borderline trades are EXACTLY the training data you need | More losing trades (expected on paper). That's the POINT - need both wins and losses for ML training | YES
Lower agents_required_to_agree | 3 of 6 | 2 of 6 | 2-3x more trades. Currently many good signals die because 1 agent disagrees. On paper, we want to test if those 3-agree and 2-agree trades differ in outcome | Lower conviction trades taken. Good for data, bad for live. Track agreement count per trade for analysis | YES
Increase max_positions | 12 | 20 | Allows more concurrent positions = more trades before hitting cap. On a $1M paper account this is fine | More capital deployed at once. Paper account - no real risk | YES
Reduce risk_pct_per_trade | 4% | 2% | Smaller positions means less impact per trade AND more room for total positions before hitting limits | Smaller individual trades. Combined with max_positions=20, total exposure similar | YES
Reduce scan intervals | 5 min (prime), 10 min (standard) | 3 min (prime), 5 min (standard) | 60-70% more scans per day. More chances to catch signals | More API calls to yfinance/TV (risk of throttling). Mitigated by IBKR streaming migration | YES
Widen TV pre-filter | RSI 42-58 killed, change < 0.3% killed | RSI 35-65, change > 0.1% | 2-3x more symbols pass to scoring. Catches mean-reversion and early breakout setups that current filter drops | More yfinance calls (slower scan if not parallelized). Fix scan speed first | YES
Enable CHOPPY regime trading | Skips momentum scans 3-4 in CHOPPY | Run all 6 scans in all regimes | In choppy markets, gap and volume scans still find opportunities. Currently Decifer sits idle in choppy markets = lost data | More trades in unfavorable conditions. Perfect for learning what NOT to trade | YES
Lower sentinel_min_confidence | 5 | 3 | 2x more sentinel trades. Currently Claude needs confidence >= 5 to fire. Lower threshold = more news-driven trades for analysis | More false positives from news. Track confidence vs outcome to find optimal threshold later | YES
Reduce sentinel cooldown | 10 min | 5 min | Can re-trigger same symbol faster if new material news arrives within window | Might double-enter same catalyst. Add position check to prevent | YES

## Social Sentiment Plan
Component | Details | Cost | Build Time | Integration Point
Reddit Sentiment Integration (VIABLE - FREE)
Data Source: Reddit JSON | GET https://www.reddit.com/r/wallstreetbets/new.json?limit=100 — returns 100 newest posts with title, score, num_comments, created_utc. No API key needed for .json endpoints | FREE | 1 day | news_sentinel.py - add as source #4
Ticker Extraction | Regex for $TICKER or all-caps 2-5 letter words that match known ticker list. Filter out common words (CEO, SEC, IPO, etc.) | FREE | 2-3 hours | NEW: reddit_sentiment.py
Mention Velocity | Track mentions per symbol per hour. ACCELERATION of mentions (not raw count) is the alpha signal. Spike from 2/hr to 20/hr = something is happening | FREE | 3-4 hours | reddit_sentiment.py
Sentiment Scoring | VADER SentimentIntensityAnalyzer + finance lexicon (moon=+3, tendies=+2, bearish=-3, rug pull=-4). Compound score per post, aggregate per symbol | FREE | 3-4 hours | reddit_sentiment.py
Claude Confirmation | For high-velocity spikes: send top 5 posts to Claude for nuanced analysis. Reuse existing claude_sentiment() from news.py. Add 'reddit' as source tag | ~$0.01/check | 2-3 hours | news_sentinel.py - deep_read_trigger
Integration | Add reddit_scan() to NewsSentinel._loop() alongside Yahoo/Finviz/IBKR. Trigger on: mention_velocity > 3x baseline AND sentiment magnitude > 0.3. Feed into existing materiality filter | FREE | 3-4 hours | news_sentinel.py
Dedup with News | Same headline sentiment on Reddit AND Yahoo RSS = stronger signal. Different sentiment = noise. Track agreement across sources | FREE | 1-2 hours | news_sentinel.py
Backtest Validation | ApeWisdom has historical trending data. Cross-reference with price moves to validate: does WSB mention velocity actually predict next-day returns for Decifer's universe? | FREE | 1 day | Uses backtester
ApeWisdom API (SHORTCUT - Pre-Computed)
Single API Call | GET https://apewisdom.io/api/v1.0/filter/all-stocks — returns top ~200 mentioned tickers with: rank, ticker, name, mentions (24h), upvotes (24h) | FREE | 2-3 hours | news_sentinel.py
Mention Spike Detection | Poll every 30 min. Compare current mentions vs 24hr rolling average. Spike > 2x baseline = trigger. Already computed by ApeWisdom so no local tracking needed | FREE | 1-2 hours | news_sentinel.py
Universe Enrichment | If a symbol appears in ApeWisdom top 50 AND your TradingView scan, it gets a social_score bonus in confluence scoring. Retail attention + institutional volume = strong signal | FREE | 2-3 hours | signals.py - add social_score dimension
RISKS & MITIGATIONS
Noise / Meme Garbage | WSB is 90% noise. Rocket emojis and YOLO posts don't predict anything. Only VELOCITY of mentions + cross-source confirmation has alpha | N/A | N/A | Use velocity (acceleration), not raw count. Require Yahoo/IBKR news confirmation
Reddit Rate Limiting | Reddit can throttle or block if you hit too hard. Typical: 100 req/min without auth, 60/min with OAuth | N/A | N/A | Poll every 60 seconds (not 30). Cache results. Use ApeWisdom as primary, Reddit JSON as backup
Stale Data (ApeWisdom) | ApeWisdom updates ~every 30 min. By the time you see a spike, fast movers may have already priced it in | N/A | N/A | Use ApeWisdom for universe discovery (which tickers to watch). Use direct Reddit JSON for real-time velocity on those tickers
Overfitting to WSB | If you trade every WSB mention, you'll catch pump-and-dumps. Many WSB picks are already at the top | N/A | N/A | Social signal is dimension 8 in scoring (0-10 points), not a standalone trigger. Must ALSO pass technical + agent filters